## Slide 1
Doaa Ahmed Gharib.
Doaa Atef Muhammed.
Doaa Othman Muhammed.

## Slide 2
Project Name: Vision Partner.
Project Sponsor: Ministry of health.
(Ministry of Health. Egypt@gmail.com). (01020304050)
Project Manager: Eng. Muhammed Salah.
(01000203040)
Project Purpose:
Helping blind people to live their lives as normal.
Business Case:
This application was created to help the blind or visually impaired.
It combines the power of
technology and human communication to deliver assistance to the blind through live video calls.
The application works by pairing blind users with sighted volunteers according to language. The first volunteer to respond to the request calls the specified user and receives a live video call through the back camera of that user's smartphone.
The application services are available for free, and only require an internet connection. You can call at any time of the day whenever you need. The sheer size of the volunteer community means that most calls are answered within 10 seconds. The blind can use it through sound by using smart phone. The blind can use this application to find the lost things, describe photos and paintings, watching or describing colors, read labels.

## Slide 3
Project Budget, Assumptions, and constraints:
  The project does not take more than 4 months.
  The cost no more 150,000$.
  Using the modern technology in the application.
Project Resources:
  Engineers, lab, devices, programmers, Database administrators, testers, and Digital marketer.
High-level risks:
- The application is not compatible with the type of mobile phone.
None of the volunteers responded to the blind person's request.
Inappropriateness of the volunteer to the requester for assistance.

## Slide 4
Scope:
  Scope description:
    A non-profit charitable application.
    Available in 80 languages.
    More than one million volunteers.
  Acceptance Criteria:
    This application requires a smart phone that supports voice and video calls.
    The app is available via IOS and Android devices.
    If a volunteer does not respond, the application can respond in some cases.
    If the call is delayed for more than 1 minute; a voice message will be sent to the user.
  Deliverables:
    Mobile application.
  Exclusions:
    Some older devices do not support this app.

## Slide 5
WBS Dictionary:
Planning:
  1.1. Specify the project goals and its budget:
    1.1.1. Description: determine the project goals and the budget available for it.
    1.1.2. Person: the project manager.
    1.1.3. Resources required: engineers, and sponsor. 1.1.4. Cost: 15.000$.
1.1.5. Milestone schedule: 2 weeks.
  1.2. Study the entire project:
    1.2.1. Description: make some experiments and exercises to study the project more clearly.
    1.2.2. Person: team leaders.
    1.2.3. Resources required: lab, devices.
1.2.4. Cost: 20.000$
1.2.5. Milestone schedule: 2 weeks.
  1.3. Specify project requirements:
    1.3.1. Description: determine and provide requirements that the project need.
    1.3.2. Person: team leaders.
    1.3.3. Resources required: engineers.
    1.3.4. Cost: 20.000$.
1.3.5. Milestone schedule: 3 weeks.

## Slide 6
Execution:
  2.1. Assign the team:
    2.1.1. Description: Built a team of people who are able to implement this project.
    2.1.2. Person: the project manager, and team leaders.
    2.1.3. Resources required: engineers, programmers. 2.1.4. Cost: 10.000$.
2.1.5. Milestone schedule: 2 weeks.
  2.2. Make a project implementation plan:
    2.2.1. Description: implementation the project plan to achieve its goal.
    2.2.2. Person: team leaders.
    2.2.3. Resources required: programmers, devices.
    2.2.4. Cost: 30.000$.
2.2.5. Milestone schedule: 3 weeks.
  2.3. Built the application code, and the project design:
    2.3.1. Description: built the code and make the design of the application.
    2.3.2. Person: project manager.
    2.3.3. Resources required: programmers, devices, and Database administrators.
2.3.4. Cost: 30.000$
2.3.5. Milestone schedule: 3 weeks.

## Slide 7
Project launch:
  3.1. Test the project:
    3.1.1. Description: testing the project before launching it to make sure everything goes perfectly.
    3.1.2. Person: team leaders.
    3.1.3. Resources required: testers.
3.1.4. Cost: 10.000$
3.1.5. Milestone schedule: 2 weeks.
  3.2. Project announcement and its feedback:
    3.2.1. Description: announcing the project, launching it in different locations, and make its feedback.
    3.2.2. Person: project manager, and team leaders.
    3.2.3. Resources required: digital marketer. 3.2.4. Cost: 15.000$.
3.2.5. Duration: 1week.

## Slide 8
Responsibility Matrices:
Project manager |  | Team Leader | Sponsor | programmer | Database administrator | Designer | Tester | Digital marketer
programming |  |  |  | C |  |  | R | 
Database |  |  |  |  | C |  | R | 
Design | R+A | P |  |  |  | C |  | 
Test project |  | P |  | P | P |  | C | 
Announcement | A | R | A |  |  | P |  | C
lunch project | A | P | P+A |  |  | P |  | P
A | Approve
C | Create
R | Revision
P | Participate

## Slide 9
Network
AUTOMATED WAREHOUSE Order Picking System |  |  | 
Activity | Description | Preceding Activity | Activity Time
A | Specify goals | None | 2 Week
B | Study Project | A | 2
C | Specify requirements | A | 3
D | Assign Team | B | 2
E | Implementation plan | C | 3
F | Code software | D, E | 3
G | Test Project | F | 2
H | Project announcement | G | 1

## Slide 10
2 | B | 4
2 | Study Project | 
4 | 2 | 6
4 | D | 6
2 | Assign Team | 
6 | 2 | 8
8 | F | 11
0 | Code software | 
8 | 3 | 11
0 | A | 2
0 | Specify goals | 
0 | 2 | 2
13 | H | 14
0 | Project announcement | 
13 | 1 | 14
11 | G | 13
0 | Test Project | 
11 | 2 | 13
2 | C |  | 5
0 | Specify requirements |  | 
2 | 3 | 5 | 
5 | E | 8
0 | Implementation plan | 
5 | 3 | 8

## Slide 11
Resource available:
Resou
rce av
ailab
le
3p
3p 3
p 3
3p
3p 3
p 3
3p
3p
p 3
p 3p
3p
3p 3
p
ID | RES | DUR | ES | LF | SL | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
A | 2P | 2 | 0 | 2 | 0 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B | 2P | 2 | 2 5 | 6 | 2 -1 |  |  | x | x | x | 2 | 2 |  |  |  |  |  |  |  |  | 
C | 2P | 3 | 2 | 5 | 0 |  |  | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  | 
D | 1P | 2 | 4 | 8 | 2 |  |  |  |  | 1 | 1 |  |  |  |  |  |  |  |  |  | 
E | 1P | 3 | 5 6 | 8 | 0 -1 |  |  |  |  |  | x | 1 | 1 | 1 |  |  |  |  |  |  | 
F | 3P | 3 | 8 9 | 11 | 0 -1 |  |  |  |  |  |  |  |  | x | 3 | 3 | 3 |  |  |  | 
G | 2P | 2 | 11 12 | 13 | 0 -1 |  |  |  |  |  |  |  |  |  |  |  | x | 2 | 2 |  | 
H | 2P | 1 | 13 14 | 14 | 0 -1 |  |  |  |  |  |  |  |  |  |  |  |  |  | x | 2 | 
Total Resource Load |  |  |  |  |  | 2p | 2p | 2p | 2p | 3p | 3p | 3p | 1p | 1p | 3p | 3p | 3p | 2p | 2p | 2p | 
Resource available |  |  |  |  |  | 3p | 3p | 3p | 3p | 3p | 3p | 3p | 3p | 3p | 3p | 3p | 3p | 3p | 3p | 3p | 3p

## Slide 12: Baseline budget:
35
50
60
80
95
90
115
121
125
133
135
150
15
10
0
20
40
60
80
100
120
140
160
1
2
3
4
5
6
7
8
9
10
11
12
13
14
Budget
Commutative baseline budget
line

## Slide 13
Risk Management:
- Risks:
- The application is not compatible with the type of mobile phone.
None of the volunteers responded to the blind person's request.
Inappropriateness of the volunteer to the requester for assistance.
To deal with these risks:
  The application supports both Android and IOS systems.
  The app supports auto reply in some cases.
  The application supports an unlimited number of calls.
To monitor the project:
- Make meetings periodically to follow up on the progress of the project.
- Make some developments on the project according to users' opinions to ensure complete user convenience.